## Backlog
Product Backlog – Data Analysis Project
Document Title: Product Backlog
Activity ID: M1.3
Date: 5-4-2025
Project Team ID: TP706– S1 – 2
Project Team Name: Team 2
Product Backlog Table
Item ID | Backlog Item | Type | Priority (P1 / P2 / P3) | Owner
DP-01 | Research and identify potential review datasets | Data Prepration | P1 | Aankit
DC-01 | Collect datasets from different sources | Data Collection | P1 | Aankit
DC-02 | Evaluate and compare datasets based on quality, completeness, and relevance | Data Collection | P2
DC-03 | Select final dataset based on analysis and project goals | Data Collection | P2
DP-01 | Design database schema to accommodate raw and cleaned data | Data Prepration | P1
DP-02 | Create and initialize the database | Data Prepration | P2
DP-03 | Validate data types and schema consistency before and after ingestion | Data Prepration | P2 | Aankit
DP-04 | Ingest the selected dataset into the database | Data Prepration | P2
DPc-01 | Remove duplicate reviews and entries | Data Preprocessing | P1
DPc-02 | Handle missing values in text, rating, or user data | Data Preprocessing | P1
DPc-03 | Detect and resolve language inconsistencies | Data Preprocessing | P3
DPc-04 | Detect and remove irrelevant reviews | Data Preprocessing | P3
DPc-05 | Clean textual data | Data Preprocessing | P1
DPc-06 | Normalize reviews (lowercasing, punctuation removal, tokenization) | Data Preprocessing | P1
DPc-07 | Remove stopwords and perform stemming/lemmatization | Stemming Prepration | P1
DP-08 | Store preprocessed and cleaned data separately | Data Prepration | P1
DA-01 | Perform exploratory data analysis | Data Analytics | P2
DP-02 | Store preprocessed and cleaned data separately | Data Prepration | P2
DA-02 | Generate visual insights | Data Analytics | P2 | Aankit
BA-01 | Build an interactive dashboard | Business Analytics | P2
BA-01 | Create summary report with business insights | Business Analytics | P2 | Aankit